**Proposed Schedule for CVPIA Near-term Restoration Strategy (NTRS)**

**For Science Integration Team Review 9/15/20**

The following is a proposed scheduled for SIT activities over the five-year term of the NTRS.

**General SIT Meeting Schedule**

* In-person meeting in March and October
* Bimonthly conference calls

**Year Zero (2020): Finalize NTRS for FY21–25**

* **SIT Oct meeting**:
  + Finalize NTRS, including addenda from SIT members
  + Decide on direction for proposed model changes

**Year One (2021): Model Development Year**

* **Modelers (winter)**:
  + Refactor models based on model changes
* **SIT March meeting**:
  + Present prototype model changes to SIT, discuss
* **Modelers (spring/summer)**:
  + Integrate model updates, calibrate model, do sensitivity analysis.
  + Subgroup reviews Model Calibration / Sensitivity Analysis (assess whether the model is still sound).
  + Run existing 13+ strategies through revised model.
* **SIT Oct meeting**:
  + Hear results of the review of Model Calibration / Sensitivity Analysis (leads to release of new version of the model).
  + Discuss results of running current strategies through the model -- based on results, determine whether existing priorities should remain or be altered.
  + Start developing ideas on new candidate strategies.
* **SIT members (winter)**:
  + Use new web tool (planned) to explore candidate strategy ideas and model output
* *Capture results in annual Adaptive Management Update*

**Year Two (2022): Recommendations Year**

* **SIT Jan call**:
  + **F**urther develop candidate strategies
* **Modelers (winter)**:
  + Draft model run of candidate strategies
* **SIT March meeting**:
  + Review results of candidate strategies
  + Determine revised set of priorities
* **Modelers (spring)**: revise model based on feedback and do final model run
* **SIT calls (summer)**:
  + Finalize updates to priorities
  + Present proposed model changes
* **SIT Oct meeting**:
  + Decide on direction for proposed model changes
* *Capture results in annual Adaptive Management Update*

**Year Three (2023): Model Development Year**

* Same as Year 1

**Year Four (2024): Recommendations Year**

* Same as Year 2; revised recommendations form the basis for next NTRS

**Year Five (2025): Complete Next Near-term Restoration Strategy (FY26–30)**

* Complete the next version of the NTRS with recommended priorities for restoration actions and information needs